## Standup meeting
Sprint | US ID | Date | Day | Assigned To | Points Discussed | Impediments | Action Taken
1 | US4,5 | 30/12/2021 | 1 | manoj,sreenidhi | UI page-- listing all available items | ui bugs | few adjustements in css part
|  |  | 1 | syed,venkatesh | integration of admin pages with springboot and API related to it | whitelabel and 404 not found error | used different properties of thmleaf
|  |  | 1 | aishwarya,laskshmanan | tried devops tools for sample project | NA | NA
2 | US6,7 | 31/12/2021 | 2 | manoj,sreenidhi,aishwarya | UI page-- listing deleting and editing exsisting item | ui bugs | changes in css and js
|  |  | 2 | syed,venkatesh | integration of admin pages with springboot and API related to it | not mapping data with mysql | adding few annotation in entity class to map
3 | US 6,7 | 2022-03-01 | 3 | manoj,sreenidhi,aishwarya | UI page-- display all CRUD in single page | ui bugs | changes in css and js
|  |  | 3 | syed,venkatesh,lakshmanan | integration of admin pages with springboot and API related to it | not able to send dynamic data to html page | referred thymleaf documents and stackoverflow
4 | US 8,9 | 2022-04-01 | 4 | aishwarya,sreenidhi,manoj | setting machine to run jenkins and nexus | unable to build jar due to unstable project maven build | referred stackoverflow
|  |  | 4 | manoj,lakshmanan,syed | job triggered to create jar for the project | unable to build jar due to unstable project maven build | referred stackoverflow
5 | US 13 | 2022-05-01 | 5 | Manoj,aishwarya,sreenidhi | docker installation and run the container | issues in connecting with mysql image | referred stackoverflow
|  |  | 5 | syed | jar using maven build | faced issue in creating jar | fixed by changing specs in pom.xml
6 | US 10,14 | 2022-06-01 | 6 | manoj,sreenidhi | UI page-- listing all available items | NA | NA
|  |  | 6 | syed,venkatesh | integration of admin pages with springboot and API related to it | issue in mapping the entity of admin class to repository | add @column and specified name
|  |  | 6 | aishwarya,laskshmanan | ansible concepts | refused connection to nodes | used keygen in authorized keys
7 | US 11,12 | 2022-07-01 | 7 | manoj,sreenidhi,aishwarya | UI page-- listing all available items | NA | NA
|  |  | 7 | syed,venkatesh,lakshmanan | integration of admin pages with springboot and API related to it | NA | NA
8 | US 15 16 | 2022-10-01 | 8 | syed,venkatesh,sreenidhi | integration of pages and creating APIs | loading the image in page through thymleaf | converting from blob to base.64 readable in html
|  |  | 8 | manoj,aishwarya | collections in mongodb | NA | NA
9 | US 17,18 | 2022-11-01 | 9 | syed,venkatesh,sreenidhi | add option to add in cart and edit | NA | NA
|  |  | 9 | manoj,aishwarya,laskshamanan | kubernets demo | NA | NA
10 | US 19,20 | 2022-12-01 | 10 | manoj,aishwarya | all admin crud operation | NA | NA
|  |  | 10 | venkatesh,syed,sreenidhi | editing the existing page to display | unable to build jar due to unstable project maven build | referred stackoverflow
11 | US 19,21 | 13/01/22 | 11 | manoj,aishwarya | api’s for user cart and delete operations | NA | NA
|  |  | 11 | venkatesh,syed,sreenidhi | integration of pages and creating APIs | id was null while id was sent from frontend to backend | referred stackoverflow and changed @Id in to generate random number in table
|  |  | 11 | lakshamanan | UI pages | NA | NA
12 | US 22,23,24 | 17/01/22 | 12 | manoj,sreenidhi | UI pages-payment | NA | NA
|  |  | 12 | syed,venkatesh | spring boot backend and integration | NA | NA
|  |  | 12 | lakshamanan | Kafka-producers | NA | NA
|  |  | 12 | aishwarya | presentation slides | NA | NA
continued…
13 | US 22,23,24 | 18/01/22 | 12 | manoj,sreenidhi | UI pages-sucess | NA | NA
|  |  | 12 | syed,venkatesh | spring boot backend and integration | unable to build jar due to unstable project maven build | referred stackoverflow
|  |  | 12 | lakshamanan | Kafka-consumer | NA | NA
|  |  | 12 | aishwarya | presentation slides | NA | NA
14 | US 22,23,24 | 19/01/22 | 13 | syed,sreenidhi,venkatesh | improvments in all frontend and toggle options | NA | NA
|  |  | 13 | manoj,aishwarya | presentaion slides | NA | NA

## Product backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | User Story Point | Assignee | Status
1 | 1 | 1 | admin: login page | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 2 | user: login page | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 3 | user: signup page | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 4 | Admin: add new item to database | Must-have |  | Frontend-manoj,shrenidhi springboot-syed,venkatesh | completed
|  | 5 | Admin: edit exisiting new item to database | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 6 | Admin: delete an existing item | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 7 | Admin: retrieve the all available data | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 8 | setting up jenkins job and connecting to nexus repo | Must-have |  | aishwarya and manoj | completed
|  | 9 | triggering the jeninks job when changes central build and push jar to nexus repo | Must-have |  | aishwarya and manoj | completed
|  | 10 | user: selecting category of his choice | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 11 | user: add item to his cart page | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | started
|  | 12 | User : adding items to cart | Must-have |  | UI-manoj springboot-syed,venkatesh | started
|  | 13 | Docker: used project jar to run container | Must-have |  | Aishwarya,manoj,shreenidhi,syed | completed
|  | 14 | Ansible: installation all basic commands | may -have |  | laksmanan | completed
|  | 15 | user: add item to his cart by giving quantity | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 16 | MongoDB- creating collections | may -have |  | Aishwarya,manoj | completed
|  | 17 | kubernets demo | may -have |  | Aishwarya,manoj | completed
|  | 18 | user: change quantity in cart table | Must-have |  | Frontend-lakshmanam,shrenidhi springboot-syed,venkatesh | completed
|  | 19 | Swagger- creating all Admin CRUD api’s | Must-have |  | Aishwarya,manoj | completed
|  | 20 | admin: add image along add new product and retrive while showing item | Must-have |  | venkatesh, syed,shrenidhi | completed
|  | 21 | user: buy now option in user cart | Must-have |  | springboot-syed,venkatesh | completed
|  | 22 | user: payement page | Must-have |  | UI-manoj springboot-syed,venkatesh,sreenidhi | completed
|  | 23 | user : success page | Must-have |  | UI-manoj springboot-syed,venkatesh,sreenidhi | completed
|  | 24 | kafka: producer and consumer | Must-have |  | laksmanan | completed
Note on F1: Kindly refrain from providing more than 8 points to user stories
Note on H1: Can be one from IN PROGRESS, COMPLETED, NOT STARTED

## sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Assiginee | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
[8 empty] | 59.5 | 0 | 0 | 0 | 0 | 0
US1 | 1 | Managing source code with Git & publishing final build using Maven | 27-12 | 27-12 | venkatesh | Buliding | completed | 0.5
| 2 | Adding validators to user inputs | 29-12 | 29-12 | manoj | coding | completed | 0.5
| 3 | coding the persistence tier |  |  | syed | coding | completed | 1
| 4 | Developing UI page |  |  | lakshmanan,aishwarya,shreenidhi | Buliding | completed | 1
US2,US3 | 1 | Managing source code with Git & publishing final build using Maven | 28-12 | 28-12 | venkatesh | Buliding | completed | 0.5
| 2 | Adding validators to user inputs | 29-12 | 29-12 | manoj | coding | completed | 0.5
| 3 | coding the persistence tier |  |  | syed | coding | completed | 1
| 4 | Developing UI page |  |  | lakshmanan,aishwarya,shreenidhi | Buliding | completed | 1
US4,5,6,7 | 1 | Developing UI pages all CRUD ops | 30-12 | 31-12 | manoj,aishwarya,shreenidhi | Buliding | completed | 5
| 2 | integration of all CRUD ops with springboot | 30-12 | 31-12 | venkatesh,syed | coding | completed | 5
| 3 | Testing all functionality | 3-1-2022 | 3-1-2022 | manoj | testing | completed | 1
US8,9 | 1 | setting up jenkins and nexus in ec2 instances | 3-1-2022 | 4-1-2022 | aishwarya,manoj | building | completed | 3
| 2 | trigging job from git and pushing jar to nexus repo | 4-1-2022 | 4-1-2022 | manoj,aishwarya | coding | completed | 2
US10,11,12 | 1 | creating model class for user | 6-1-2022 | 6-1-2022 | syed,venkatesh,sreenidhi | coding | completed | 2
| 2 | selecting categories part by user | 6-1-2022 | 6-1-2022 | syed,venkatesh,sreenidhi,manoj | coding | completed | 2
| 3 | add to cart option for user |  |  | syed,venkatesh | coding | working
| 4 | items selected by user(his cart) |  |  | syed,venkatesh | coding | working
US13 | 1 | setting machine for docker | 5-1-2022 | 6-1-2022 | aishwarya,manoj | building | completed | 1
| 2 | setting up docker container for jar of project | 5-1-2022 | 6-1-2022 | aishwarya,manoj,syed,sreenidhi | building | completed | 2
US 14 | 1 | installing ansible and run commands | 7-1-2022 | 7-1-2022 | lakshmanan | building | completed | 2
US15 | 1 | creating model class for user | 2022-10-01 | 2022-11-01 | syed,venkatesh,sreenidhi | coding | completed | 2
| 2 | selecting categories part by user | 2022-10-01 | 2022-11-01 | syed,venkatesh,sreenidhi,manoj | coding | completed | 2
| 3 | add to cart option for user | 2022-10-01 | 2022-11-01 | syed,venkatesh | coding | working | 1
US 16 | 1 | creating all collections | 2022-10-01 | 2022-11-01 | aishwarya,manoj | building | completed | 2
US 17 | 1 | kubernets demo | 2022-11-01 | 2022-11-01 | aishwarya,manoj | building | completed | 2
US18 | 1 | UI pages for editing and add quantity | 2022-11-01 | 2022-11-01 | sreenidhi,lakshmanan | building | completed | 2
| 2 | springboot backend and integration | 2022-11-01 | 2022-11-01 | syed,venkatesh | building | completed | 1.5
US 19 | 1 | swagger- CRUD for admin | 2022-12-01 | 2022-12-01 | aishwarya,manoj | building | completed | 2.5
| 2 | Swagger- api’s for user | 13/01/22 | 13/01/22 | aishwarya,manoj | building | completed | 1
US 20 | 1 | upload image from admin implementation in springboot | 2022-12-01 | 2022-12-01 | syed,venkatesh | building | completed | 2
| 2 | editing the existing page to display | 2022-12-01 | 2022-12-01 | sreenidhi | building | completed | 2
US 21 | 1 | UI pages for editing item | 13/01/22 | 13/01/22 | lakshmanan | building | completed | 1
| 2 | springboot backend and integration | 13/01/22 | 13/01/22 | syed,venkatesh | building | completed | 2.5
US 22,23 | 1 | payment and success UI | 17/01/22 | 18/01/22 | UI-manoj,sreenidhi | building | completed | 1.5
| 2 | integration and springboot | 17/01/22 | 18/01/22 | springboot-syed,venkatesh | building | completed | 2
US 24 | 1 | kafka producer and consumer | 17/01/22 | 17/01/22 | lakshmanan | building | completed | 1.5
Note on C4: This is a one time job and the time estimation for this job should be done by single trainee per group only once. For other User stories this task should have a value '0'.
Note on C9: This is a one time job and the time estimation for this job should be done by single trainee per group only once. For other User stories this task should have a value '0'.
Note on I2: This is the total task estimated in hours for all the user stories. Total estimation effort cannot be more than 120 hours
Note on J2: Pending effort hours after completion of day 1 work
Note on K2: Pending effort hours after completion of day 2 work
Note on L2: Pending effort hours after completion of day 3 work
Note on M2: Pending effort hours after completion of day 4 work
Note on N2: Pending effort hours after completion of day 5 work